## Sheet1
Autopilot hints	done (mission 1 & 2)
Glide hints
Armor table + piercing effect	Done
Script that toggles sync fire?		Sabre
Recharge shields & guns between nav points		Excalibur
		Thunderbolt
Missions
Name	System	Fighter	Hints	Dialogue skips	Checkpoint	Energy Recharge	Else	If WCS ever up to date

M01-BG-Hermes.fs2	Brimstone 1	Hellcat	Autopilot	None

M02-BG-Hermes.fs2	Brimstone 2	Hellcat	Autopilot	None
			+ Comm menu

M03-BG-Hermes.fs2	Brimstone 3	Hellcat	Bombs & bomber targeting	Done – mission start dialogue

M04-BG-Hermes.fs2	Brimstone 4 ->Vega	Longbow	None	None		None

M05-BG-Hermes.fs2	Vega 1	Hellcat	F12 to target incoming fighters @ corvette nav	Done – Fort Crockett dialogue skippable		Done	Charlie engages fighters if they get too close @ corvette nav	Afterburn to corvettes?
			Added Fireclaw to escort list					Scripted bombing run?

M06-BG-Hermes.fs2	Vega 2	Hellcat	None	None		None

M07-BG-Hermes.fs2	Vega 3	Hellcat	None	None

M08-BG-Hermes.fs2	Vega 4	Hellcat	None	When meeting the valks
				After blasting the missiles

M09-BG-Hermes.fs2	Vega 5	Hellcat	Autopilot	Before autopilot link
				After missile strike

M10-BG-Hermes.fs2	Proxima 1	Arrow	Glide toggle	None		Done
			Afterburn before gliding
			Glide to save fuel

M11-BG-Hermes.fs2	Proxima 2	Arrow	None	At convoy jump point before and after arrival		Done
				After the ghost kitties disappear

M12-BG-Hermes.fs2	Proxima 3	Arrow	None	Before nav 4

M13-BG-Hermes.fs2	Proxima 4	Arrow	Display/hide transfer status	When meeting the Langley			TODO: make Alpha engages incoming fighters sooner during transfer
				Before transfer

M14-BG-Hermes.fs2	Loki 1		None	TODO:before entering the asteroid field

M15-BG-Hermes.fs2	Loki 2		None	TODO:before nav4

M16-BG-Hermes.fs2	Loki 3		None

M17-BG-Hermes.fs2

M18-BG-Hermes.fs2

M19-BG-Hermes.fs2

M20-BG-Hermes.fs2

M21-BG-Hermes.fs2

M22-BG-Hermes.fs2

M23-BG-Hermes.fs2

M24-BG-Hermes.fs2

M25-BG-Hermes.fs2

M26-BG-Hermes.fs2

M27-BG-Hermes.fs2

M28-BG-Hermes.fs2

M29-BG-Hermes.fs2

M30-BG-Hermes.fs2

M31-BG-Hermes.fs2

M32-BG-Hermes.fs2

M33-BG-Hermes.fs2

M34-BG-Hermes.fs2

M35-BG-Hermes.fs2

M36-BG-Hermes.fs2

M37-BG-Hermes.fs2

M38-BG-Hermes.fs2

M39-BG-Hermes.fs2

M40-BG-Hermes.fs2

M41-BG-Hermes.fs2

M42-BG-Hermes.fs2

M43-BG-Hermes.fs2

M44-BG-Hermes.fs2

M45-BG-Hermes.fs2

M46-BG-Hermes.fs2

M47-BG-Hermes.fs2

M48-BG-Hermes.fs2

M49-BG-Hermes.fs2

M50-BG-Hermes.fs2